## Tasks
Task | Priority | Owner | Status | Blocked by | Start date | End date | Deliverable | Notes
Framework for App | P1 | All | In progress
DB for App | P1 | Ineh | In progress
Research Backend Frameworks/ Technologies for APP | P1 | Yoga | In progress |  | 2025-01-17 | 2025-01-18
Wireframes and Simple Designs | P2 | Yiran | In progress |  | 2025-01-19
Meeting Journal Updates | P2 | Yiran | In progress |  | 2025-01-20
Task Journal Updates | P2 | Yoga | In progress |  | 2025-01-23

## Meeting Journal
Purpose | Date/Time | Attendees | Notes
Initial Meeting between members | 2025-01-17 | Ineh, Yiran, Yoga | All the team members have met. We have nominated a SCRUM Master, a DB Admin, and a Product Manager. We have created a few tasks on the board and started working on those.
First Standup to complete Lab 2 | 2025-01-20 | Ineh, Yiran, Yoga | We discussed the wireframe design and the front-end platform to use and decided on Flutter. We assigned more roles to each member and finished our first draft of ICA.

## Team Member Roles
Name | Role
Yiran | Product Manager
Developer
Co-Author
Editor
QA Engineer
Ineh | DB Admin
Developer
Author Major Document
QA Engineer
Yoga | Scrum master
Developer
QA Engineer
Team Lead
Client liaison
Repository Monitor

## Contract
https://docs.google.com/document/d/1Q9_czpT9DS6vL8XBoqUghq19QZ7vfa1-UzQV2Dsu3NA/edit?usp=sharing
Note
Document Version | 1
Team Name | Dynamic Trio
Team Members | Yiran, Ineh, Yoga
Team Preferred communication | Discord, Teams Meetings, Outlook Mails
Official Repository | https://github.com/Srinivas142000/DT-MedRhythm
Team Organization (discussed in lecture) | Agile Team with 3 members
Weekly standup day/time | Monday - 10:00 AM to 11:00 AM
Expectations statement (discussed in lecture) | Roles totalling >100 points for each member
By Adding my name below this line I acknowledge that I agree to the above responsibilities assigned to me and I understand. Type your name/date here. Putting anyone else’s name here will be considered academic dishonesty.
Primary author: | Yoga Srinivas Reddy Kasireddy
Member 2: | Ineh Ifeanyi Robert
Member 3: | Yiran Zhao
Member 4:
Version Log

## Project artifacts
Artifact | Version | Added | Link | Team comment | Instructor comment | Accepted and Graded
Project Repo | 1 | Yes | https://github.com/Srinivas142000/DT-MedRhythm |  |  | FALSE
SRS | [5 empty] | FALSE
SDD | [5 empty] | FALSE
Testing | 1 |  |  |  |  | FALSE
Testing | 2 |  |  |  |  | FALSE
Project Score Sheet | 1 | Yes | DT - Medrhythms Scoring Sheet |  |  | FALSE
Team Member Assignment and Submission Sheet | 1 | Yes | SE - Team Member Assignments |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## ICA 1 - Suggested Point System
Task/Role | Description | Point Value
Author major document | primary/only author for the SRS, SDD, or testing document Only 1 allowed per document | 40 Points
Author minor document | primary/only author for any minor document Only 1 allowed per document | 15 Points
Co-Author | Secondary author on a document that is complex enough to require it | 30 Points
Editor | Reviewer of a document | 20 Points
Software developer - primary | Major contributor to the final application Numer allowed depends on the size and complexity of the final product | 40 Points
Software developer - secondary contributor | Contributor to the final application, but not the primary contributor | 20 Points
Tester | Final application tester | 20 Points
Team Lead | Team lead if your team organization requires one | 20 Points
Client liaison | Primary liaison for the client | 15 Points
Repository Monitor | Keeper of the repository and monitor | 10 Points

## ICA 2 - Individual Assessment
Team Member | Product (if applicable) | Assignment Num | Role | Points
Yiran | Drew the wireframe design of the app, researched the frontend technology to use | Lab 2 | Developer | 40
Yiran |  |  | Co-Author | 30
Yiran |  |  | Editor | 20
Yiran |  |  | Tester | 20
Ineh | Researched on what database to use as the DB admin, Researched on Frontend technology as well | Lab 2 | Developer | 40
Ineh |  |  | Author | 40
Ineh |  |  | Tester | 20
Yoga | Created Repository | Lab 2 | Repository Monitor
Yoga | Sent a mail to client to schedule meeting | Lab 2 | Client liaison
Yoga | Researched Backend Technologies to use |  | Developer

## Other Links
Software Requirements Specification
Software Design Document
https://github.com/Srinivas142000/DT-MedRhythm
SE - Team Member Assignments